## A23SC_OLD
Measure A Capital Projects
Quarterly Status Report
PROJECT INFO
|  | Quarter Ended: |  |  |  | September 30, 2022 | [8 empty] | Fiscal Year: | 2022-23 |  |  |  | Reporting Quarter: |  |  |  | 1
| Agency: |  | County of Sacramento | [11 empty] | Project Mgr: | Tim Stevens, Senior Civil Engineer
[15 empty] | Contact Info: | (916) 874-6291
Project Name: |  |  | Hazel Avenue: US Highway 50 Interchange and Folsom Blvd Intersection
[5 empty] | Sponsor Project ID Number: | STRL41 | [11 empty] | STA Project ID Number: | A-23-SC
[5 empty] | Original Est. Project Cost: | $ | 61268182 | [10 empty] | Current Est. Project Cost: | $ | 105000000
MEASURE A FUNDING
[5 empty] | Previous Contract(s) Amount: | $ | 1679031.22 | [8 empty] | Projected Spending |  | 2 | $ | 1300000
[5 empty] | Previous Contract(s) Spending: | $ | 1679031.22 | [10 empty] | 3 | $ | 1300000
[5 empty] | Current Contract Amount: | $ | 6821000 | [10 empty] | 4 | $ | 1300000
[5 empty] | Current Contract Spending: | $ | 253172.3 | [10 empty] | 1 | $ | 335000
[5 empty] | Expended This Quarter: | $ | 0
[5 empty] | Total Remaining: | $ | 6567827.7 | [6 empty] | Funds leveraged using local match | [6 empty] | $ | 926189
PROJECT STATUS
|  | Start Date | [14 empty] | Comp. Date (orig) |  |  |  |  | Comp. Date (current)
|  | 2009-07-01 |  |  |  |  | Indicate overall progress on the bar below | [9 empty] | 2018-01-01 |  |  |  |  | 2027-10-31
|  |  |  | 5% |  | 15% |  | 25% |  | 35% |  | 45% |  | 55% |  | 65% |  | 75% |  | 85% |  | 95%
Progress:
|  |  | 0% |  | 10% |  | 20% |  | 30% |  | 40% |  | 50% |  | 60% |  | 70% |  | 80% |  | 90% |  | 100%
Current Status (as of last day of reporting quarter; check only one):
Explanation of Activities this Quarter and Additional Notes
Note on I21: Dustin Purinton: Reallocation on 9/30/22
Note on I24: Dustin Purinton: Agreed
Not Started
Pending or On-Hold
Design and/or Engineering
Right-of-Way Acquisition
Environmental Review
Planning/Financing/Approval
Bidding and/or Contracting
Under Construction
Completed
The Value Analysis Study was completed and consultant is refining preliminary design to address items that were identified in the study. Topo survey and boundary mapping continue this quarter and are expected to be complete in November. Real Estate acquisitions to begin in 2023.

## A23SC_NEW
Measure A Capital Projects
Quarterly Status Report
|  |  | Quarter Ended: |  |  |  | September 30, 2022 | [8 empty] | Fiscal Year: | 2022-23 |  |  |  | Reporting Quarter: |  |  |  | 1
|  | Agency: |  | County of Sacramento | [11 empty] | Project Mgr: | Tim Stevens, Senior Civil Engineer
[16 empty] | Phone and Email: | (916) 874-6291, stevensti@saccounty.net
| Project Name: |  |  | Hazel Avenue: US Highway 50 Interchange and Folsom Blvd Intersection
Project Description:
This project proposes to construct safety and access improvements at the US Highway 50 / Hazel Avenue interchange and the Hazel Avenue/Folsom Boulevard intersection. Proposed improvements include modifications to the interchange structure and freeway ramps; extension of Hazel Avenue south of US 50 and Folsom Boulevard; construction of a grade separation at the Hazel Avenue/Folsom Boulevard intersection to separate the Hazel Avenue extension from Folsom Boulevard and the light rail tracks; and construction of a connection road to provide new access between Folsom Boulevard and the Hazel Avenue extension. The project also includes a multi-use path from the American River Parkway south across US 50 and Folsom Boulevard.
[6 empty] | Sponsor Project ID Number: | STRL41 | [11 empty] | STA Project ID Number: | A-23-SC
[6 empty] | Original Est. Project Cost: | $ | 61268182 | [10 empty] | Current Est. Project Cost: | $ | 105000000
MEASURE A CAPITAL FUNDING
[6 empty] | Previous Contract(s) Amount: | $ | 1679031.22 | [8 empty] | Projected Spending |  | 2 | $ | 1300000
[6 empty] | Previous Contract(s) Spending: | $ | 1679031.22 | [10 empty] | 3 | $ | 1300000
[6 empty] | Current Contract Amount: | $ | 6821000 | [10 empty] | 4 | $ | 1300000
[6 empty] | Current Contract Spending: | $ | 253172.3 | [10 empty] | 1 | $ | 335000
[6 empty] | Expended This Quarter: | $ | 0
[6 empty] | Total Remaining: | $ | 6567827.7 | [6 empty] | Funds leveraged using Measure A: | [6 empty] | $ | 926189
| PROJECT MILESTONES | [11 empty] | Begin |  |  |  |  | Planned Completion |  |  |  |  | Completed
Project Study
Environmental (PA&ED) Phase
Design (PS&E) Phase
Right-of-Way Phase
Construction Phase
| Current Phase (as of last day of reporting quarter; check only one): | [12 empty] | Environmental (PA&ED) Phase
Indicate overall progress of the current phase
[5 empty] | 5% |  | 15% |  | 25% |  | 35% |  | 45% |  | 55% |  | 65% |  | 75% |  | 85% |  | 95%
Progress:
|  |  |  | 0% |  | 10% |  | 20% |  | 30% |  | 40% |  | 50% |  | 60% |  | 70% |  | 80% |  | 90% |  | 100%
Explanation of Activities and Expenditures this Quarter, Next Quarter, and Additional Notes
Current Quarter: The Value Analysis Study was completed and consultant is refining preliminary design to address items that were identified in the study. Topo survey and boundary mapping continue this quarter and are expected to be complete in November.
Next Quarter: Topo survey and boundary mapping to be complete in November.
Additional Notes: Real Estate acquisitions to begin in 2023.
Column1
Project Study Phase
Environmental (PA&ED) Phase
Design (PS&E) Phase
Right-of-Way Phase
Bidding Phase
Construction Phase
Construction Complete
Pending or On-Hold
Not Started

## A05SC not started (hidden)
Measure A Capital Projects
Quarterly Status Report
PROJECT INFO
Status Report for Quarter Ended: |  |  |  |  | September 30, 2016 | [8 empty] | Fiscal Year: | 2016/17 |  |  |  | Reporting Quarter: |  |  |  | 1
Project Sponsor: |  | County of Sacramento | [11 empty] | Project Mgr: | Refugio Razo, Senior Civil Engineer
Project Name: |  | Arden Way ITS, Phase 2 – Ethan Road to Fair Oaks Blvd
|  |  |  | Sponsor Project ID Number: | [12 empty] | STA Project ID Number: | A-05-SC
|  |  |  | Original Estimated Project Cost: | $ | 3467693 | [10 empty] | Current Estimated Project Cost: | $ | 3467693
MEASURE A FUNDING
|  |  |  | Measure A Allocation Amount: | $ | 1734000 | [6 empty] | Projected Spending Over the Next Three Quarters |  |  |  | 2 | $
|  |  |  | Total Previously Expended: | $ | [9 empty] | à |  | 3 | $
|  |  |  | Expended This Quarter: | $ | [11 empty] | 4 | $
|  |  |  | Total Remaining: | $ | 1734000 | [6 empty] | Measure A Funds Used for Local Match?
PROJECT STATUS
Completed Tasks (check all that apply):
| Start Date | [19 empty] | (Projected) Completion Date
Indicate overall progress on the bar below:
|  |  | 5% |  | 15% |  | 25% |  | 35% |  | 45% |  | 55% |  | 65% |  | 75% |  | 85% |  | 95%
Progress:
|  | 0% |  | 10% |  | 20% |  | 30% |  | 40% |  | 50% |  | 60% |  | 70% |  | 80% |  | 90% |  | 100%
Activity this Quarter (check all that apply):
Current Status (as of last day of reporting quarter; check only one):
Notes/Expand Details (only if necessary)
Additional Notes (will not print)
Yes
No
Design & Engineering
Planning/Financing/Approvals
Environmental Clearance
Right-of-Way Acquisition
Bidding & Contracting
Construction
Other:
Design/Engineering
Planning/Financing/Approvals
Environmental Review
Right-of-Way Acquisition
Bidding/Contracting
Construction
Other:
Not Started
Pending or On-Hold
Design and/or Engineering
Right-of-Way Acquisition
Environmental Review
Planning/Financing/Approval
Bidding and/or Contracting
Under Construction
Completed

## A07SC completed (hidden)
Measure A Capital Projects
Quarterly Status Report
PROJECT INFO
Status Report for Quarter Ended: |  |  |  |  | September 30, 2016 | [8 empty] | Fiscal Year: | 2016/17 |  |  |  | Reporting Quarter: |  |  |  | 1
Project Sponsor: |  | County of Sacramento | [11 empty] | Project Mgr: | John Jaeger, Senior Civil Engineer
Project Name: |  | Bradshaw Road Improvements, Phase 1 – Calvine Road to Florin Road
|  |  |  | Sponsor Project ID Number: | ST0TRC | [11 empty] | STA Project ID Number: | A-07-SC
|  |  |  | Original Estimated Project Cost: | $ | 15282111 | [10 empty] | Current Estimated Project Cost: | $ | 21500000
MEASURE A FUNDING
|  |  |  | Measure A Allocation Amount: | $ | 8525000 | [6 empty] | Projected Spending Over the Next Three Quarters |  |  |  | 2 | $
|  |  |  | Total Previously Expended: | $ | 8525000 | [8 empty] | à |  | 3 | $
|  |  |  | Expended This Quarter: | $ | [11 empty] | 4 | $
|  |  |  | Total Remaining: | $ | 0 | [6 empty] | Measure A Funds Used for Local Match?
PROJECT STATUS
Completed Tasks (check all that apply):
| Start Date | [19 empty] | (Projected) Completion Date
| 1997-01-01 |  |  |  |  | Indicate overall progress on the bar below: | [14 empty] | 2012-12-31
|  |  | 5% |  | 15% |  | 25% |  | 35% |  | 45% |  | 55% |  | 65% |  | 75% |  | 85% |  | 95%
Progress:
|  | 0% |  | 10% |  | 20% |  | 30% |  | 40% |  | 50% |  | 60% |  | 70% |  | 80% |  | 90% |  | 100%
Activity this Quarter (check all that apply):
Current Status (as of last day of reporting quarter; check only one):
Notes/Expand Details (only if necessary)
This project started prior to the approval of the new Measure A renewal. The project widened the existing roadway from 2 to 4 lanes including a landscaped roadway median and traffic signal modifications.
Additional Notes (will not print)
Yes
No
Design & Engineering
Planning/Financing/Approvals
Environmental Clearance
Right-of-Way Acquisition
Bidding & Contracting
Construction
Other:
Design/Engineering
Planning/Financing/Approvals
Environmental Review
Right-of-Way Acquisition
Bidding/Contracting
Construction
Other:
Not Started
Pending or On-Hold
Design and/or Engineering
Right-of-Way Acquisition
Environmental Review
Planning/Financing/Approval
Bidding and/or Contracting
Under Construction
Completed

## A08SC not started (hidden)
Measure A Capital Projects
Quarterly Status Report
PROJECT INFO
Status Report for Quarter Ended: |  |  |  |  | September 30, 2016 | [8 empty] | Fiscal Year: | 2016/17 |  |  |  | Reporting Quarter: |  |  |  | 1
Project Sponsor: |  | County of Sacramento | [11 empty] | Project Mgr: | Refugio Razo, Senior Civil Engineer
Project Name: |  | Bradshaw Road Improvements, Phase 2 – Corridor Enhancements
|  |  |  | Sponsor Project ID Number: | [12 empty] | STA Project ID Number: | A-08-SC
|  |  |  | Original Estimated Project Cost: | $ | 197395083 | [10 empty] | Current Estimated Project Cost: | $ | 197395083
MEASURE A FUNDING
|  |  |  | Measure A Allocation Amount: | $ | 65764000 | [6 empty] | Projected Spending Over the Next Three Quarters |  |  |  | 2 | $
|  |  |  | Total Previously Expended: | $ | [9 empty] | à |  | 3 | $
|  |  |  | Expended This Quarter: | $ | [11 empty] | 4 | $
|  |  |  | Total Remaining: | $ | 65764000 | [6 empty] | Measure A Funds Used for Local Match?
PROJECT STATUS
Completed Tasks (check all that apply):
| Start Date | [19 empty] | (Projected) Completion Date
Indicate overall progress on the bar below:
|  |  | 5% |  | 15% |  | 25% |  | 35% |  | 45% |  | 55% |  | 65% |  | 75% |  | 85% |  | 95%
Progress:
|  | 0% |  | 10% |  | 20% |  | 30% |  | 40% |  | 50% |  | 60% |  | 70% |  | 80% |  | 90% |  | 100%
Activity this Quarter (check all that apply):
Current Status (as of last day of reporting quarter; check only one):
Notes/Expand Details (only if necessary)
Additional Notes (will not print)
Yes
No
Design & Engineering
Planning/Financing/Approvals
Environmental Clearance
Right-of-Way Acquisition
Bidding & Contracting
Construction
Other:
Design/Engineering
Planning/Financing/Approvals
Environmental Review
Right-of-Way Acquisition
Bidding/Contracting
Construction
Other:
Not Started
Pending or On-Hold
Design and/or Engineering
Right-of-Way Acquisition
Environmental Review
Planning/Financing/Approval
Bidding and/or Contracting
Under Construction
Completed

## A13SC not started (hidden)
Measure A Capital Projects
Quarterly Status Report
PROJECT INFO
Status Report for Quarter Ended: |  |  |  |  | September 30, 2016 | [8 empty] | Fiscal Year: | 2016/17 |  |  |  | Reporting Quarter: |  |  |  | 1
Project Sponsor: |  | County of Sacramento | [11 empty] | Project Mgr: | Refugio Razo, Senior Civil Engineer
Project Name: |  | Folsom Blvd Improvements – Watt Avenue to Bradshaw Road
|  |  |  | Sponsor Project ID Number: | [12 empty] | STA Project ID Number: | A-13-SC
|  |  |  | Original Estimated Project Cost: | $ | 40698160 | [10 empty] | Current Estimated Project Cost: | $ | 40698160
MEASURE A FUNDING
|  |  |  | Measure A Allocation Amount: | $ | 13673000 | [6 empty] | Projected Spending Over the Next Three Quarters |  |  |  | 2 | $
|  |  |  | Total Previously Expended: | $ | [9 empty] | à |  | 3 | $
|  |  |  | Expended This Quarter: | $ | [11 empty] | 4 | $
|  |  |  | Total Remaining: | $ | 13673000 | [6 empty] | Measure A Funds Used for Local Match?
PROJECT STATUS
Completed Tasks (check all that apply):
| Start Date | [19 empty] | (Projected) Completion Date
Indicate overall progress on the bar below:
|  |  | 5% |  | 15% |  | 25% |  | 35% |  | 45% |  | 55% |  | 65% |  | 75% |  | 85% |  | 95%
Progress:
|  | 0% |  | 10% |  | 20% |  | 30% |  | 40% |  | 50% |  | 60% |  | 70% |  | 80% |  | 90% |  | 100%
Activity this Quarter (check all that apply):
Current Status (as of last day of reporting quarter; check only one):
Notes/Expand Details (only if necessary)
Additional Notes (will not print)
Yes
No
Design & Engineering
Planning/Financing/Approvals
Environmental Clearance
Right-of-Way Acquisition
Bidding & Contracting
Construction
Other:
Design/Engineering
Planning/Financing/Approvals
Environmental Review
Right-of-Way Acquisition
Bidding/Contracting
Construction
Other:
Not Started
Pending or On-Hold
Design and/or Engineering
Right-of-Way Acquisition
Environmental Review
Planning/Financing/Approval
Bidding and/or Contracting
Under Construction
Completed

## A17SC not started (hidden)
Measure A Capital Projects
Quarterly Status Report
PROJECT INFO
Status Report for Quarter Ended: |  |  |  |  | September 30, 2016 | [8 empty] | Fiscal Year: | 2016/17 |  |  |  | Reporting Quarter: |  |  |  | 1
Project Sponsor: |  | County of Sacramento | [11 empty] | Project Mgr: | Refugio Razo, Senior Civil Engineer
Project Name: |  | Greenback Lane Improvements – Interstate 80 to Manzanita Avenue
|  |  |  | Sponsor Project ID Number: | [12 empty] | STA Project ID Number: | A-17-SC
|  |  |  | Original Estimated Project Cost: | $ | 12892748 | [10 empty] | Current Estimated Project Cost: | $ | 12892748
MEASURE A FUNDING
|  |  |  | Measure A Allocation Amount: | $ | 4242000 | [6 empty] | Projected Spending Over the Next Three Quarters |  |  |  | 2 | $
|  |  |  | Total Previously Expended: | $ | [9 empty] | à |  | 3 | $
|  |  |  | Expended This Quarter: | $ | [11 empty] | 4 | $
|  |  |  | Total Remaining: | $ | 4242000 | [6 empty] | Measure A Funds Used for Local Match?
PROJECT STATUS
Completed Tasks (check all that apply):
| Start Date | [19 empty] | (Projected) Completion Date
Indicate overall progress on the bar below:
|  |  | 5% |  | 15% |  | 25% |  | 35% |  | 45% |  | 55% |  | 65% |  | 75% |  | 85% |  | 95%
Progress:
|  | 0% |  | 10% |  | 20% |  | 30% |  | 40% |  | 50% |  | 60% |  | 70% |  | 80% |  | 90% |  | 100%
Activity this Quarter (check all that apply):
Current Status (as of last day of reporting quarter; check only one):
Notes/Expand Details (only if necessary)
Additional Notes (will not print)
Yes
No
Design & Engineering
Planning/Financing/Approvals
Environmental Clearance
Right-of-Way Acquisition
Bidding & Contracting
Construction
Other:
Design/Engineering
Planning/Financing/Approvals
Environmental Review
Right-of-Way Acquisition
Bidding/Contracting
Construction
Other:
Not Started
Pending or On-Hold
Design and/or Engineering
Right-of-Way Acquisition
Environmental Review
Planning/Financing/Approval
Bidding and/or Contracting
Under Construction
Completed

## A19SC not started (hidden)
Measure A Capital Projects
Quarterly Status Report
PROJECT INFO
Status Report for Quarter Ended: |  |  |  |  | September 30, 2016 | [8 empty] | Fiscal Year: | 2016/17 |  |  |  | Reporting Quarter: |  |  |  | 1
Project Sponsor: |  | County of Sacramento | [11 empty] | Project Mgr: | Refugio Razo, Senior Civil Engineer
Project Name: |  | Greenback Lane Widening, Phase 1 – Fair Oak Blvd to Hazel Avenue
|  |  |  | Sponsor Project ID Number: | [12 empty] | STA Project ID Number: | A-19-SC
|  |  |  | Original Estimated Project Cost: | $ | 29377373 | [10 empty] | Current Estimated Project Cost: | $ | 29377373
MEASURE A FUNDING
|  |  |  | Measure A Allocation Amount: | $ | 12412000 | [6 empty] | Projected Spending Over the Next Three Quarters |  |  |  | 2 | $
|  |  |  | Total Previously Expended: | $ | [9 empty] | à |  | 3 | $
|  |  |  | Expended This Quarter: | $ | [11 empty] | 4 | $
|  |  |  | Total Remaining: | $ | 12412000 | [6 empty] | Measure A Funds Used for Local Match?
PROJECT STATUS
Completed Tasks (check all that apply):
| Start Date | [19 empty] | (Projected) Completion Date
Indicate overall progress on the bar below:
|  |  | 5% |  | 15% |  | 25% |  | 35% |  | 45% |  | 55% |  | 65% |  | 75% |  | 85% |  | 95%
Progress:
|  | 0% |  | 10% |  | 20% |  | 30% |  | 40% |  | 50% |  | 60% |  | 70% |  | 80% |  | 90% |  | 100%
Activity this Quarter (check all that apply):
Current Status (as of last day of reporting quarter; check only one):
Notes/Expand Details (only if necessary)
Additional Notes (will not print)
Yes
No
Design & Engineering
Planning/Financing/Approvals
Environmental Clearance
Right-of-Way Acquisition
Bidding & Contracting
Construction
Other:
Design/Engineering
Planning/Financing/Approvals
Environmental Review
Right-of-Way Acquisition
Bidding/Contracting
Construction
Other:
Not Started
Pending or On-Hold
Design and/or Engineering
Right-of-Way Acquisition
Environmental Review
Planning/Financing/Approval
Bidding and/or Contracting
Under Construction
Completed

## A20SC not started (hidden)
Measure A Capital Projects
Quarterly Status Report
PROJECT INFO
Status Report for Quarter Ended: |  |  |  |  | September 30, 2016 | [8 empty] | Fiscal Year: | 2016/17 |  |  |  | Reporting Quarter: |  |  |  | 1
Project Sponsor: |  | County of Sacramento | [11 empty] | Project Mgr: | Refugio Razo, Senior Civil Engineer
Project Name: |  | Greenback Lane Widening, Phase 2 – Hazel Avenue to Main Street
|  |  |  | Sponsor Project ID Number: | [12 empty] | STA Project ID Number: | A-20-SC
|  |  |  | Original Estimated Project Cost: | $ | 22844829 | [10 empty] | Current Estimated Project Cost: | $ | 22844829
MEASURE A FUNDING
|  |  |  | Measure A Allocation Amount: | $ | 8099000 | [6 empty] | Projected Spending Over the Next Three Quarters |  |  |  | 2 | $
|  |  |  | Total Previously Expended: | $ | [9 empty] | à |  | 3 | $
|  |  |  | Expended This Quarter: | $ | [11 empty] | 4 | $
|  |  |  | Total Remaining: | $ | 8099000 | [6 empty] | Measure A Funds Used for Local Match?
PROJECT STATUS
Completed Tasks (check all that apply):
| Start Date | [19 empty] | (Projected) Completion Date
Indicate overall progress on the bar below:
|  |  | 5% |  | 15% |  | 25% |  | 35% |  | 45% |  | 55% |  | 65% |  | 75% |  | 85% |  | 95%
Progress:
|  | 0% |  | 10% |  | 20% |  | 30% |  | 40% |  | 50% |  | 60% |  | 70% |  | 80% |  | 90% |  | 100%
Activity this Quarter (check all that apply):
Current Status (as of last day of reporting quarter; check only one):
Notes/Expand Details (only if necessary)
Additional Notes (will not print)
Yes
No
Design & Engineering
Planning/Financing/Approvals
Environmental Clearance
Right-of-Way Acquisition
Bidding & Contracting
Construction
Other:
Design/Engineering
Planning/Financing/Approvals
Environmental Review
Right-of-Way Acquisition
Bidding/Contracting
Construction
Other:
Not Started
Pending or On-Hold
Design and/or Engineering
Right-of-Way Acquisition
Environmental Review
Planning/Financing/Approval
Bidding and/or Contracting
Under Construction
Completed

## A23SC not started (hidden)
Measure A Capital Projects
Quarterly Status Report
PROJECT INFO
Status Report for Quarter Ended: |  |  |  |  | September 30, 2016 | [8 empty] | Fiscal Year: | 2016/17 |  |  |  | Reporting Quarter: |  |  |  | 1
Project Sponsor: |  | County of Sacramento | [11 empty] | Project Mgr: | Refugio Razo, Senior Civil Engineer
Project Name: |  | Hazel Avenue Improvements, Phase 2 – Corridor Enhancements
|  |  |  | Sponsor Project ID Number: | [12 empty] | STA Project ID Number: | A-23-SC
|  |  |  | Original Estimated Project Cost: | $ | 105006897 | [10 empty] | Current Estimated Project Cost: | $ | 105006897
MEASURE A FUNDING
|  |  |  | Measure A Allocation Amount: | $ | 34819000 | [6 empty] | Projected Spending Over the Next Three Quarters |  |  |  | 2 | $
|  |  |  | Total Previously Expended: | $ | [9 empty] | à |  | 3 | $
|  |  |  | Expended This Quarter: | $ | [11 empty] | 4 | $
|  |  |  | Total Remaining: | $ | 34819000 | [6 empty] | Measure A Funds Used for Local Match?
PROJECT STATUS
Completed Tasks (check all that apply):
| Start Date | [19 empty] | (Projected) Completion Date
Indicate overall progress on the bar below:
|  |  | 5% |  | 15% |  | 25% |  | 35% |  | 45% |  | 55% |  | 65% |  | 75% |  | 85% |  | 95%
Progress:
|  | 0% |  | 10% |  | 20% |  | 30% |  | 40% |  | 50% |  | 60% |  | 70% |  | 80% |  | 90% |  | 100%
Activity this Quarter (check all that apply):
Current Status (as of last day of reporting quarter; check only one):
Notes/Expand Details (only if necessary)
Additional Notes (will not print)
Yes
No
Design & Engineering
Planning/Financing/Approvals
Environmental Clearance
Right-of-Way Acquisition
Bidding & Contracting
Construction
Other:
Design/Engineering
Planning/Financing/Approvals
Environmental Review
Right-of-Way Acquisition
Bidding/Contracting
Construction
Other:
Not Started
Pending or On-Hold
Design and/or Engineering
Right-of-Way Acquisition
Environmental Review
Planning/Financing/Approval
Bidding and/or Contracting
Under Construction
Completed

## A25SC not started (hidden)
Measure A Capital Projects
Quarterly Status Report
PROJECT INFO
Status Report for Quarter Ended: |  |  |  |  | September 30, 2016 | [8 empty] | Fiscal Year: | 2016/17 |  |  |  | Reporting Quarter: |  |  |  | 1
Project Sponsor: |  | County of Sacramento | [11 empty] | Project Mgr: | Refugio Razo, Senior Civil Engineer
Project Name: |  | Madison Avenue Improvements, Phase 2 – Hazel Avenue to Greenback Lane
|  |  |  | Sponsor Project ID Number: | [12 empty] | STA Project ID Number: | A-25-SC
|  |  |  | Original Estimated Project Cost: | $ | 22361625 | [10 empty] | Current Estimated Project Cost: | $ | 22361325
MEASURE A FUNDING
|  |  |  | Measure A Allocation Amount: | $ | 8097000 | [6 empty] | Projected Spending Over the Next Three Quarters |  |  |  | 2 | $
|  |  |  | Total Previously Expended: | $ | [9 empty] | à |  | 3 | $
|  |  |  | Expended This Quarter: | $ | [11 empty] | 4 | $
|  |  |  | Total Remaining: | $ | 8097000 | [6 empty] | Measure A Funds Used for Local Match?
PROJECT STATUS
Completed Tasks (check all that apply):
| Start Date | [19 empty] | (Projected) Completion Date
Indicate overall progress on the bar below:
|  |  | 5% |  | 15% |  | 25% |  | 35% |  | 45% |  | 55% |  | 65% |  | 75% |  | 85% |  | 95%
Progress:
|  | 0% |  | 10% |  | 20% |  | 30% |  | 40% |  | 50% |  | 60% |  | 70% |  | 80% |  | 90% |  | 100%
Activity this Quarter (check all that apply):
Current Status (as of last day of reporting quarter; check only one):
Notes/Expand Details (only if necessary)
Additional Notes (will not print)
Yes
No
Design & Engineering
Planning/Financing/Approvals
Environmental Clearance
Right-of-Way Acquisition
Bidding & Contracting
Construction
Other:
Design/Engineering
Planning/Financing/Approvals
Environmental Review
Right-of-Way Acquisition
Bidding/Contracting
Construction
Other:
Not Started
Pending or On-Hold
Design and/or Engineering
Right-of-Way Acquisition
Environmental Review
Planning/Financing/Approval
Bidding and/or Contracting
Under Construction
Completed

## A26SC not started (hidden)
Measure A Capital Projects
Quarterly Status Report
PROJECT INFO
Status Report for Quarter Ended: |  |  |  |  | September 30, 2016 | [8 empty] | Fiscal Year: | 2016/17 |  |  |  | Reporting Quarter: |  |  |  | 1
Project Sponsor: |  | County of Sacramento | [11 empty] | Project Mgr: | Refugio Razo, Senior Civil Engineer
Project Name: |  | Madison Avenue Improvements, Phase 3 – Watt Avenue to Sunrise Blvd
|  |  |  | Sponsor Project ID Number: | [12 empty] | STA Project ID Number: | A-26-SC
|  |  |  | Original Estimated Project Cost: | $ | 61566990 | [10 empty] | Current Estimated Project Cost: | $ | 61566990
MEASURE A FUNDING
|  |  |  | Measure A Allocation Amount: | $ | 20397000 | [6 empty] | Projected Spending Over the Next Three Quarters |  |  |  | 2 | $
|  |  |  | Total Previously Expended: | $ | 0 | [8 empty] | à |  | 3 | $
|  |  |  | Expended This Quarter: | $ | 0 | [10 empty] | 4 | $
|  |  |  | Total Remaining: | $ | 20397000 | [6 empty] | Measure A Funds Used for Local Match?
PROJECT STATUS
Completed Tasks (check all that apply):
| Start Date | [19 empty] | (Projected) Completion Date
Indicate overall progress on the bar below:
|  |  | 5% |  | 15% |  | 25% |  | 35% |  | 45% |  | 55% |  | 65% |  | 75% |  | 85% |  | 95%
Progress:
|  | 0% |  | 10% |  | 20% |  | 30% |  | 40% |  | 50% |  | 60% |  | 70% |  | 80% |  | 90% |  | 100%
Activity this Quarter (check all that apply):
Current Status (as of last day of reporting quarter; check only one):
Notes/Expand Details (only if necessary)
Additional Notes (will not print)
Yes
No
Design & Engineering
Planning/Financing/Approvals
Environmental Clearance
Right-of-Way Acquisition
Bidding & Contracting
Construction
Other:
Design/Engineering
Planning/Financing/Approvals
Environmental Review
Right-of-Way Acquisition
Bidding/Contracting
Construction
Other:
Not Started
Pending or On-Hold
Design and/or Engineering
Right-of-Way Acquisition
Environmental Review
Planning/Financing/Approval
Bidding and/or Contracting
Under Construction
Completed

## A28SC not started (hidden)
Measure A Capital Projects
Quarterly Status Report
PROJECT INFO
Status Report for Quarter Ended: |  |  |  |  | September 30, 2016 | [8 empty] | Fiscal Year: | 2016/17 |  |  |  | Reporting Quarter: |  |  |  | 1
Project Sponsor: |  | County of Sacramento | [11 empty] | Project Mgr: | Refugio Razo, Senior Civil Engineer
Project Name: |  | South Watt Avenue/Elk Grove-Florin Road Improvements, Phase 2 – Folsom Blvd to Calvine Road
|  |  |  | Sponsor Project ID Number: | [12 empty] | STA Project ID Number: | A-28-SC
|  |  |  | Original Estimated Project Cost: | $ | 222238144 | [10 empty] | Current Estimated Project Cost: | $ | 222238144
MEASURE A FUNDING
|  |  |  | Measure A Allocation Amount: | $ | 74150000 | [6 empty] | Projected Spending Over the Next Three Quarters |  |  |  | 2 | $
|  |  |  | Total Previously Expended: | $ | [9 empty] | à |  | 3 | $
|  |  |  | Expended This Quarter: | $ | [11 empty] | 4 | $
|  |  |  | Total Remaining: | $ | 74150000 | [6 empty] | Measure A Funds Used for Local Match?
PROJECT STATUS
Completed Tasks (check all that apply):
| Start Date | [19 empty] | (Projected) Completion Date
Indicate overall progress on the bar below:
|  |  | 5% |  | 15% |  | 25% |  | 35% |  | 45% |  | 55% |  | 65% |  | 75% |  | 85% |  | 95%
Progress:
|  | 0% |  | 10% |  | 20% |  | 30% |  | 40% |  | 50% |  | 60% |  | 70% |  | 80% |  | 90% |  | 100%
Activity this Quarter (check all that apply):
Current Status (as of last day of reporting quarter; check only one):
Notes/Expand Details (only if necessary)
Additional Notes (will not print)
Yes
No
Design & Engineering
Planning/Financing/Approvals
Environmental Clearance
Right-of-Way Acquisition
Bidding & Contracting
Construction
Other:
Design/Engineering
Planning/Financing/Approvals
Environmental Review
Right-of-Way Acquisition
Bidding/Contracting
Construction
Other:
Not Started
Pending or On-Hold
Design and/or Engineering
Right-of-Way Acquisition
Environmental Review
Planning/Financing/Approval
Bidding and/or Contracting
Under Construction
Completed

## A31SC not started (hidden)
Measure A Capital Projects
Quarterly Status Report
PROJECT INFO
Status Report for Quarter Ended: |  |  |  |  | September 30, 2016 | [8 empty] | Fiscal Year: | 2016/17 |  |  |  | Reporting Quarter: |  |  |  | 1
Project Sponsor: |  | County of Sacramento | [11 empty] | Project Mgr: | Refugio Razo, Senior Civil Engineer
Project Name: |  | Sunrise Blvd Improvements – Jackson Road to Grant Line Road
|  |  |  | Sponsor Project ID Number: | [12 empty] | STA Project ID Number: | A-31-SC
|  |  |  | Original Estimated Project Cost: | $ | 54900000 | [10 empty] | Current Estimated Project Cost: | $ | 79763000
MEASURE A FUNDING
|  |  |  | Measure A Allocation Amount: | $ | 1500000 | [6 empty] | Projected Spending Over the Next Three Quarters |  |  |  | 2 | $ | 0
|  |  |  | Total Previously Expended: | $ | 0 | [8 empty] | à |  | 3 | $ | 0
|  |  |  | Expended This Quarter: | $ | 0 | [10 empty] | 4 | $ | 0
|  |  |  | Total Remaining: | $ | 1500000 | [6 empty] | Measure A Funds Used for Local Match?
PROJECT STATUS
Completed Tasks (check all that apply):
Project is programmed, but not assigned to design staff.
| Start Date | [19 empty] | (Projected) Completion Date
Indicate overall progress on the bar below:
|  |  | 5% |  | 15% |  | 25% |  | 35% |  | 45% |  | 55% |  | 65% |  | 75% |  | 85% |  | 95%
Progress:
|  | 0% |  | 10% |  | 20% |  | 30% |  | 40% |  | 50% |  | 60% |  | 70% |  | 80% |  | 90% |  | 100%
Activity this Quarter (check all that apply):
No Activities this quarter.
Current Status (as of last day of reporting quarter; check only one):
Notes/Expand Details (only if necessary)
Measure A funds allocated to this project. Start date will be determined at a later date.
Additional Notes (will not print)
Yes
No
Design & Engineering
Planning/Financing/Approvals
Environmental Clearance
Right-of-Way Acquisition
Bidding & Contracting
Construction
Other:
Design/Engineering
Planning/Financing/Approvals
Environmental Review
Right-of-Way Acquisition
Bidding/Contracting
Construction
Other:
Not Started
Pending or On-Hold
Design and/or Engineering
Right-of-Way Acquisition
Environmental Review
Planning/Financing/Approval
Bidding and/or Contracting
Under Construction
Completed

## A33SC not started (hidden)
Measure A Capital Projects
Quarterly Status Report
PROJECT INFO
Status Report for Quarter Ended: |  |  |  |  | September 30, 2016 | [8 empty] | Fiscal Year: | 2016/17 |  |  |  | Reporting Quarter: |  |  |  | 1
Project Sponsor: |  | County of Sacramento | [11 empty] | Project Mgr: | Refugio Razo, Senior Civil Engineer
Project Name: |  | Sunrise Blvd Improvements – Madison Avenue to Gold Country Road
|  |  |  | Sponsor Project ID Number: | [12 empty] | STA Project ID Number: | A-33-SC
|  |  |  | Original Estimated Project Cost: | $ | 23128065 | [10 empty] | Current Estimated Project Cost: | $ | 23128065
MEASURE A FUNDING
|  |  |  | Measure A Allocation Amount: | $ | 9191000 | [6 empty] | Projected Spending Over the Next Three Quarters |  |  |  | 2 | $
|  |  |  | Total Previously Expended: | $ | [9 empty] | à |  | 3 | $
|  |  |  | Expended This Quarter: | $ | [11 empty] | 4 | $
|  |  |  | Total Remaining: | $ | 9191000 | [6 empty] | Measure A Funds Used for Local Match?
PROJECT STATUS
Completed Tasks (check all that apply):
| Start Date | [19 empty] | (Projected) Completion Date
Indicate overall progress on the bar below:
|  |  | 5% |  | 15% |  | 25% |  | 35% |  | 45% |  | 55% |  | 65% |  | 75% |  | 85% |  | 95%
Progress:
|  | 0% |  | 10% |  | 20% |  | 30% |  | 40% |  | 50% |  | 60% |  | 70% |  | 80% |  | 90% |  | 100%
Activity this Quarter (check all that apply):
Current Status (as of last day of reporting quarter; check only one):
Notes/Expand Details (only if necessary)
Additional Notes (will not print)
Yes
No
Design & Engineering
Planning/Financing/Approvals
Environmental Clearance
Right-of-Way Acquisition
Bidding & Contracting
Construction
Other:
Design/Engineering
Planning/Financing/Approvals
Environmental Review
Right-of-Way Acquisition
Bidding/Contracting
Construction
Other:
Not Started
Pending or On-Hold
Design and/or Engineering
Right-of-Way Acquisition
Environmental Review
Planning/Financing/Approval
Bidding and/or Contracting
Under Construction
Completed

## A54SC completed (hidden)
Measure A Capital Projects
Quarterly Status Report
PROJECT INFO
Status Report for Quarter Ended: |  |  |  |  | September 30, 2016 | [8 empty] | Fiscal Year: | 2016/17 |  |  |  | Reporting Quarter: |  |  |  | 1
Project Sponsor: |  | County of Sacramento | [11 empty] | Project Mgr: | John Jaeger, Senior Civil Engineer
Project Name: |  | US Highway 50/Watt Avenue Interchange Upgrade
|  |  |  | Sponsor Project ID Number: | ST0TXP | [11 empty] | STA Project ID Number: | A-54-SC
|  |  |  | Original Estimated Project Cost: | $ | 29238996 | [10 empty] | Current Estimated Project Cost: | $ | 42160817
MEASURE A FUNDING
|  |  |  | Measure A Allocation Amount: | $ | 11348000 | [6 empty] | Projected Spending Over the Next Three Quarters |  |  |  | 2 | $
|  |  |  | Total Previously Expended: | $ | 11348000 | [8 empty] | à |  | 3 | $
|  |  |  | Expended This Quarter: | $ | [11 empty] | 4 | $
|  |  |  | Total Remaining: | $ | 0 | [6 empty] | Measure A Funds Used for Local Match?
PROJECT STATUS
Completed Tasks (check all that apply):
| Start Date | [19 empty] | (Projected) Completion Date
| 7/1/2002 |  |  |  |  | Indicate overall progress on the bar below: | [14 empty] | 12/31/2016
|  |  | 5% |  | 15% |  | 25% |  | 35% |  | 45% |  | 55% |  | 65% |  | 75% |  | 85% |  | 95%
Progress:
|  | 0% |  | 10% |  | 20% |  | 30% |  | 40% |  | 50% |  | 60% |  | 70% |  | 80% |  | 90% |  | 100%
Activity this Quarter (check all that apply):
Current Status (as of last day of reporting quarter; check only one):
Notes/Expand Details (only if necessary)
Additional Notes (will not print)
Yes
No
Design & Engineering
Planning/Financing/Approvals
Environmental Clearance
Right-of-Way Acquisition
Bidding & Contracting
Construction
Other:
Design/Engineering
Planning/Financing/Approvals
Environmental Review
Right-of-Way Acquisition
Bidding/Contracting
Construction
Other:
Not Started
Pending or On-Hold
Design and/or Engineering
Right-of-Way Acquisition
Environmental Review
Planning/Financing/Approval
Bidding and/or Contracting
Under Construction
Completed

## A01SC not started (hidden)
Measure A Capital Projects
Quarterly Status Report
PROJECT INFO
Status Report for Quarter Ended: |  |  |  |  | September 30, 2016 | [8 empty] | Fiscal Year: | 2016/17 |  |  |  | Reporting Quarter: |  |  |  | 1
Project Sponsor: |  | County of Sacramento | [11 empty] | Project Mgr: | Refugio Razo, Senior Civil Engineer
Project Name: |  | Antelope Road Improvements – Watt Avenue to Roseville Road
|  |  |  | Sponsor Project ID Number: | [12 empty] | STA Project ID Number: | A-01-SC
|  |  |  | Original Estimated Project Cost: | $ | 9307473 | [10 empty] | Current Estimated Project Cost: | $ | 9307473
MEASURE A FUNDING
|  |  |  | Measure A Allocation Amount: | $ | 1734000 | [6 empty] | Projected Spending Over the Next Three Quarters |  |  |  | 2 | $
|  |  |  | Total Previously Expended: | $ | [9 empty] | à |  | 3 | $
|  |  |  | Expended This Quarter: | $ | [11 empty] | 4 | $
|  |  |  | Total Remaining: | $ | 1734000 | [6 empty] | Measure A Funds Used for Local Match?
PROJECT STATUS
Completed Tasks (check all that apply):
| Start Date | [19 empty] | (Projected) Completion Date
Indicate overall progress on the bar below:
|  |  | 5% |  | 15% |  | 25% |  | 35% |  | 45% |  | 55% |  | 65% |  | 75% |  | 85% |  | 95%
Progress:
|  | 0% |  | 10% |  | 20% |  | 30% |  | 40% |  | 50% |  | 60% |  | 70% |  | 80% |  | 90% |  | 100%
Activity this Quarter (check all that apply):
Current Status (as of last day of reporting quarter; check only one):
Notes/Expand Details (only if necessary)
Additional Notes (will not print)
Yes
No
Design & Engineering
Planning/Financing/Approvals
Environmental Clearance
Right-of-Way Acquisition
Bidding & Contracting
Construction
Other:
Design/Engineering
Planning/Financing/Approvals
Environmental Review
Right-of-Way Acquisition
Bidding/Contracting
Construction
Other:
Not Started
Pending or On-Hold
Design and/or Engineering
Right-of-Way Acquisition
Environmental Review
Planning/Financing/Approval
Bidding and/or Contracting
Under Construction
Completed