## Slide 1: 2020 Local Partnership Program (Competitive) Kammerer Road Complete Reconstruction Bruceville Road to Lent Ranch Parkway
Presented by:
Kevin Bewsey, City of Elk Grove Capital Program Division Manager
May 14, 2020

## Slide 2: Project Location
Kammerer Road
Lotz Parkway.
Lent Ranch Parkway
SR-99
McMillan Road
Bruceville Road
Big Horn Boulevard
Grant Line
Road

## Slide 3: Project Summary
Reconstruct 2.5 miles of existing Kammerer Road
Two lane divided roadway
Shoulder/class III bikeway
Median or two-way left turn lanes

## Slide 4: Project Limits
Kammerer Road
Lotz Parkway.
Lent Ranch Parkway
SR-99
McMillan Road
Bruceville Road
Big Horn Boulevard
2018 SB1 LPP Grant - $3M for Construction with a $3M Local Match
2020 SB1 LPP Grant Request
2020 SB1 LPP Grant Request
Grant Line
Road

## Slide 5: Competitive Criteria
Cost Effective
  Combines two separate City projects to build at once.
Deliverability
  Projects already underway with CEQA complete and R/W offers made.
Leveraging Funds
  Leverages previous LPP competitive funds
Air Quality/GHG/VMT Reduction
  Adds a 6’ wide Class 3 bikeway in each direction.
Regional/Community Support
  Included in Existing Measure A
  Public Outreach Completed
Regional/Local Plan
  Included in the 2020 MTP/SCS

## Slide 6: Competitive Criteria, Safety and Preservation
Safety
  Adds shoulders.
System Preservation
  Reconstructs existing road.
Notes: PCI is 66, 60 west of mcmillan

## Slide 7: Project Schedule
December 2018 – Environmental Document Secured
December 2020 – ROW Acquisitions Completed
January 2021 – Advertise for Construction
Spring 2021 – Start of Construction
Fall 2021 – Construction Completed

## Slide 8: Project Cost
Total Project Cost = $25.6M
  Preliminary Engineering – $1.8M
  Other Capital Costs – $300K
  ROW – $5.8M
  Environmental – $900K
  Construction & CM - $16.8M
    2018 SB1 LPP Grant = $3M with equal $3M local match

## Slide 9: Questions